## Sheet1
90 Day Child Protection Emergency Response Plan - Abbania
Objective: The UNICEF Child Protection Programme will enhance child protection in emergency-affected areas and prevent girls and boys from violence, exploitation, unnecessary separation form family, and the effect of conflict.
Expected Outcome | Planned Activities | Indicators | Partners | Timeframe | [6 empty] | Notes/ issues for consideration/ details
|  |  |  | wk1-2 | wk3-4 | wk5-6 | wk7-8 | wk9-10 | wk11-12 | wk13-14
Expected Programme outcome/result 1: Strengthened national level CP systems in place, including laws, policies, regulations and services to suport and respond to protection-related risks and for the enhancement of the protective environment for all children in Genesis.
Legislative and policy reform to address key priorities is undertaken through the strengthening of the legal and policy frameworks for the protection of children
Strengthened services for children in contact with the law
Strengthened child welfare services for children at risk and their families
Expected Programme outcomes/result 2: Social change supported through open discussion and the transformation of harmful traditional practices, social norms and behavior to minimize children's vulnerability.
Strengthened knowledge and understanding of the cultural, social, political, and economic factors that can be harmful to children, and those that can be used to support and promote prevention and response to violence, abuse and exploitation at the community/social level.
Increased community knowledge, understanding and capcaity in relation to harmful traditional practices and customs, and other forms of violence, abuse and exploitation of children
Strengthened community-based child protection mechanisms
Expected Programme outcomes: Children affected by emergencies in Abbania protected in line with UNCEF's Core Commitments to Children in Humanitarian Action (CCC).
1. Coordination | 1. Activate the existing coordination mechanisms with the involvement of government, CBOs and NGOs and discuss key issues of child protection interventions. | Number of meetings and participants in coordination mechanism. | UNHCR, OCHA, Save the Children, local NGOs | x
| 2. Appoint the sub-national coordinators and develop the TOR and objectives of the coordination mechanism | Terms of reference for the child protection working group exists. Dedicated coordinator appointed within one week. | UNHCR, OCHA, Save the Children, local NGOs | x
| 3. Identify joint needs, and decide on roles and responsibility among protection actors in Abbenia | Number of members identified for each sub-sector, and their periodic reports. | UNHCR, OCHA, Save the Children, | x
| 4. Development of interagency strategic response plan for child protection on protection including, GBV, psychosocial interventions, mine action, separation and unaccompanied children | A documented strategic plan for the child protection response has been agreed by relevant and responsible authorities, humanitarian agencies and local civial society actors. | UNHCR, OCHA, Save the Children, local NGos | x | x
| 5. Agree on common tools for joint communication | Communication channels identified, and being used. | UNHCR, OCHA, Save the Children, local Ngos | x
| 6. Coordinate and ensure child protection is mainstreamed within other clusters: Education, WASH, Shelter, Protection | Number of meetings. Number of agreed action. | clusters on Education, WASH, Shelter and Protection
2. Child Protection Rapid Assessment in the camps and earthquake affected areas. | 1. Gather information from partners and desk review to update the situation | No. Of Sitreps submitted, exchanged. | coordination members | x
| 2. Carry out rapid assessment on CP in the camps and host communities | Percentage of surveyed children, parents or caregivers who remembers giving an informed consent before an interview. | Oxfam, Save the Children, local Ngos |  |  | x
3. separation and accompanied children | 1. Assess the scope, causes and risks of family separation |  | UNHCR, local NGOs, WFP, INGOs | x
| 2. Advocacy for prevention of family separation especially during relocation and agree on actions to prevent separation during relocation. |  | UNHCR, local NGOs, WFP, INGOs | x | x | x
| 3. Agree on standardized registration forms and SOP for IDTR. | Adapted registration forms, SOPs, information, referral and case-management systems in place within one week of emergency. | UNHCR, INGOS, local NGOs and para-social workers | x
| 4. Establish mechanisms regularly and systematically to monitor the safety and well being of UASC | Percentage of children who have received at least one follow-up visit within one month of being reunited with caregivers. | UNHCR, INGOs, local Ngos |  | x | x | x | x | x | x
| 5. Develop the referral system for seperated or missing children and raise awareness in communities and families about IDTR services | Percentage of registered UASC in appropriprate interim or long-term alternative care. | UNHCR, INGOs, local Ngos | x | x | x | x | x | x | x
| 6. Start tracing and reunification immediately and make sure that there is suffecient staff and relevant logistics requirement . | Percentage of children registered for tracing that hats been reunified and stayed with their family for more than six months. | UNHCR, INGOs, local Ngos | x | x | x | x | x | x | x
| 7. Eatablish BID process and strengthen alternative care system existing in the community. | Percentage of registered UASC in appropriate care arrangements. | UNHCR, INGO, local NGos
| 8. Establish social protection programmes such as additional food support, cash transfers, counceling for vulnerable families to prevent separation and to support foster families. | Number of social protection programmes implemented and number of families reporting prevention of separation. | UNDP, INGOs, local Ngos, |  | x
4. Psychosocial Support | 1. Identify the trained community based child protection workers and support them in the provision of psychosocial first aid. | Percentage of community based child protection workers having received the training. | INGOs, local Ngos, community based child protection groups |  | x
| 2. Establish and support the culturally appropriate recreation activities in the camps in consultation with children, families and communities. Ensure safety place and appropriate activities for young people and adolescents. Carry out assessment with community to see if CFS is needed. | Percentage of targetted communities where community-initiated activities for children are supported and take place at least once every week. | INGOs, local Ngos, community based child protection groups |  | x | x | x | x | x | x
| 3. Set up detection and referral system for mental health for children and care givers. | Percentage of targetted children in CP programmes reported to be showing a decrease in symptoms associated with mental disorders and psychosocial distress compared to the baseline. | INGOs, local Ngos, community based child protection groups |  | x | x | x | x | x | x
| 4. Provide support to care givers to improve care for their children and to deal with their own distress. | Percentage of targetted communities in which at least 50% of caregivers surveyed have received training or counselling on how to deal with psychosocial issues. | INGOs, local Ngos, community based child protection groups
5. children associated with armed forces or armed groups | 1. Work with local leaders, community groups, schools and youth organization to take action to prevent recruitment or voluntary participation in armed forces or groups. | Reduction in number of girls and boys associated with armed forces or armed groups. | UNHCR | x | x | x | x | x
| 2. Carry out public information campaigns where appropriate on the risks for children associated with armed forces or armed groups and the risk of family separation. | Percentage of humanitarian actors reporting to have seen the key messages, and can report at least two correctly. | INGOs, local Ngos, community based child protection groups
| 3. Develop the Task Force on MRM and establish a process for trained child protection staff to identify and varifiy children associated with armed forces or armed groups. | Existance of a set of interim care procedures that are agreed upon and implemented by all relevant actors. | INGOs, local Ngos, community based child protection groups
| 4. Initiate discussions with the appropriate military and armed group commanders or militia leaders at local and national level for advocate for the release of children. | Key messages drafted, delivered and being described by the key advocacy targets.
| 5. Take all boys or girls varified to be associated with armed forces or armed groups as quickly as possible to a safe civilian location, initiate family tracking process and ensure community-oriented approach for reintegration phase | Percentage of girls and boys separated from armed forces or groups who are effectively reintegrated in their families and the community or alternatively integrated. | UNHCR
6. Sexual violence | 1. Dissiminate key sexual violence prevention messages, working with children, families and communities. | Percentage of children, families and communities reporting to have received key messages, and can describe the key message. | INGOs, local Ngos, community based child protection groups
| 2. Support community based child protection groups to prevent sexual violence, identify and support sexual violence survivors using pychosocial first aid. | Number of child protection programmes that address sexual violence
| 3. Establish the age-, sex- and cultural appropriate referral pathways and services. | Percentage of reported cases of children who experienced sexual violence who received age and gender specific referrals. | Oxfam, Save the Children
| 4. provide child friendly, multi sectoral holistic care for child survivors and their families. | Percentage of CP programmes that have number of sectors covered delivering holistic care for child survivors and their families. | Oxfam, Save the Children, local NGOs
7. Landmine | 1. Production and distribution of landmine and ERW materials. | Number of ERW materials distributed, and percentage of social workers and community members able to report key messages. | Save the Children, local NGOs
| 2. Conduct mine risk education programme. | Percentage of cummunity members able to report correct messages. | existing local partners, community leaders
| 3. Landmine clearing (after the situation gets better). | UN agency responsible for land mine clearing reporting safe situation.
Effective leadership and coordination of CP, GBV and PSS, with links to other sectors on critical inter-sectoral issues. | 1.Assess existing coordination mechanisms and determine how issues of humanitarian child protection interventions can best be coordinated, including with local civil society (3W); |  | UNICEF, UNHCR, OCHA,INGOs, LNGOs, MoH |  | x |  | *
| 2.Develop a coordinated strategy for building capaity of CP workers within PSS, GBV,CP |  | UNICEF, UNHCR, OCHA,INGOs, LNGOs, MoH |  |  |  | x
| 3. Establish SOP for GBV, PSS, MRM and referal mechanism |  | UNICEF, UNHCR, OCHA,INGOs, MoH, LNGOs |  | x |  |  | x
| 4.Develop a joint preparedness or contingency plan, building on existing community structures as well as lessons learned from previous emergencies, and make sure that preparedness actions (such as staff training, translation of tools, creation of MoUs and stockpiling) are completed and up to date; |  | UNICEF, UNHCR, OCHA,INGOs, LNGOs |  | x |  | x
Effective monitoring and reporting on grave violations and other serious protection concerns, with a link to programmatic response. | 1-Establish gender-based violence (GBVIMS), and the Child Protection Information Management System (CPIMS) including a systematic review of media information, police reports etc |  | MoSW, UNHCR, INGOs, LNGOs |  | x |  | x
| 2- Train partners and establish WG for (MRM) on grave violations and other reporting mechanisms on grave violation against children |  | MoSW, UNHCR, INGOs, LNGOs | x
Strengthened community- based child protection mechanisms to respond to protectoin risks of children in emergency affected areas. | 1.Create child friendly spaces, playgrounds, and recreation areas for children and youth. 2. Include risk-reduction and risk-education messages in formal and non-formal education, recreation activities for children, and community messaging activities; |  | MoSW, UNHCR, INGOs, LNGOs, CBOs
The separation of children from their families is prevented and responded to and family based care is promoted. | 1.At risk- children or in need of protection are supported with established and operational referral mechanism adequate case management adn social protection to ensure home based care |  | MoSW, UNHCR, INGOs, LNGOs
Violence, exploitation and abuse of children and women, including GBV, are prevented and addressed. | 1. Baseline study and Capacity building of all actors and stakeholders on CPiE |  | MoSW, UNHCR, INGOs, LNGOs
| 2.Prepare child protection messages addressing likely protection risks for children (separation, sexual violence, psychosocial support, injury, etc.) and agree on a strategy to share and use them in the event of an emergency |  | MoSW, UNHCR, INGOs, LNGOs
| 3. Operationalize community based CP committees to prevent child abuse and explotation through awereness raising, child rights promotion, contribute to early identification response, reporting and referral. |  | MoSW, UNHCR, INGOs, LNGOs
Strengthened psychosocial wellbeing of children and their care givers in emergency affected areas. | 1. Enusre well trained social workers, well established referral mechanisams and case confrencing |  | MoSW, UNHCR, INGOs, LNGOs |  | x |  | *
Child recruitment and arbitrary detention of affected children is prevented and addressed. |  1. Promote coordination and cooperation among all actors working on prevention of child recruitment and use, on release of children from armed forces or groups, and on providing assistance to their reintegration |  | MoSW, UNHCR, INGOs, LNGOs
| 2. Work with local leaders, community groups, schools, and youth organizations to take action to prevent recruitment or voluntary participation in armed forces or groups;  |  | MoSW, UNHCR, INGOs, LNGOs
| 3.interactive popular theater campaignes to raise awareness |  | MoSW, UNHCR, INGOs, LNGOs
| 4. Identify and support children who are vulnerable to recruitment. Provide access to social protection and operational referral mechanisms and adeqquate case management by trained social workers |  | MoSW, UNHCR, INGOs, LNGOs
Reduced impact of landmines and other indiscriminate weapons on the community and children. | 1. MRE for children in schools and out of school and parents |  | OCHA, UNICEF,UNHCR, MoSW, INGOs, LNGOs, Military and Police