## Sheet1
Template for UNICEF 90- Day Plan
Instructions: Prepare a 90-day Child Protection Plan for all Genesis, covering all the affected areas broken down by location: Abbania, Jelton, Collinstown and vaccinity. The Plan must be consistent with UNICEF's CCCs, and should be based along the same general framework and as per the identified priorities in the Genesis Child Protection Programme AWP. At the same time, it must respond to the specific CP needs and priorities in each individual location.
Deadline and presentation format: You will be meeting with the UNICEF Representative to present your 90-day plan at 14:30 (end of day 6). She has asked be presented to her following the information template below and in line with the AWP: ie: - Overall, and geographic specific situation assessment; - Activity implementation plan as per AWP priority results areas.
TEMPLATE/Format for 90-day Plan:
1. Situation Assessment and priority issues:
1.1 Overall CP situation in the Country
1.2 CP situation in Denver
1.3 CP situation in Abbania
1.3 CP situation in Jelton
2. 90-day Implementation Plan
Expected Outputs | Planned Activities | Planned Results | Partners | Implementation period (month)
|  |  |  | 1 | 2 | 3
Country-wide
The separation of children from their families is prevented and responded to and family based care is promoted. | Based on Rapid Assessment, assess and analyse scope, causes and risks of separation (disaggregating by age, gender, disability and ethnicity) | Completed analysis available | UNICEF, UNHCR, | X
| Modify and update PCAs with World Vision, Child Fund and Oxfam to reflect changing situation in Denver regoin | Signed PCAs | WV, CF, | X
| Reach cross-sectoral and government agreement (through CP sub-cluster) on SOP - including: standardised registration forms and operating procedures for IDTR; development and sign-off on information and case management system; development of identification strategy for SUAM (registration points; community outreach; outreach to relevant services); development of referral system; | SOP developed and disseminated | GoG (Dof SW), UNHCR, ICRC, Oxfam, Word Vision, Child Fund, MSF, WFO, School for All/ Education, WASH, Health sections | X
| Set up FTR database based on established SOP | Database in place | DofSW; UNHCR; ICRC; WV; CF | X
| In collaboration with partners, identify and establish interim/alternative care strategies, prioritising community/family-based care | Stategy for alternative care documented; strateg work plan developed; |  | X
| Support partners in rollout of training with all key actors, including staff and community volunteers | # of trainings conducted |  | X
| Implement proactive strategy, based on SOPs, on identification of SUAMs, FTR and Interim care | surveillance systems in place; % of children of registered SUAM in appropriate and protective care |  | X | X | X
| Development of family separation prevention strategy (including guidance on camp reception and arrivcal areas; on population movements; and community awareness raising) | # of workshops/training; | WV, CF, | X
| Development, translation and dissemination of CD4 tools for awareness raising on prevention | # of materials disseminated | UNICEF, UNHCR, ICRC, DoSW, INGOs | X
| Work with partners on rollout of region-wide awareness raising (linking with CBCPM) | # of awareness raising sessions |  | X | X | X
| Monitor and Report on implementation | M&E templates |  | X | x | x
Denver
In-depth protection assessment
Jelton
Abbania