## Slide 1: Planificación de Programa de Espacios Amigables para Niños y Niñas

## Slide 2: Objetivos
Al final de esta sesión, los participantes…
Conocerán cómo desarrollar objetivos para su programa de Espacios Amigables para Niños y Niñas
Estarán familiarizados con dos marcos / matrices que pueden ayudar en la planificación de programas

## Slide 3: Esquema de la Sesión
Resumen de las etapas del ciclo del proyecto
Qué indica que hay necesidad de un CFS
Herramientas para la planificación de programas
  Marco lógico
  Diagrama de Gantt
Actividad de planificación

## Slide 4: Resumen de las etapas del ciclo del proyecto
Preparación
Coordinar
Hacer una evaluación
Fijar objetivos basados en la evaluación
Planificar e implementar actividades basadas en los objetivos:
  Abordar temas de servicios básicos y seguridad
  Movilizar el apoyo de la familia y la comunidad
  Desarrollar programas psicosociales estructurados (de ser necesario / posible)
  Capacitar al personal
  Establecer referencias a los servicios apropiados de salud mental
Monitorear y evaluar
Cerrar el proyecto
Notes: We are focusing here on Steps 4 & 5, how you set your objectives and then design the programme plan to meet those objectives –
Identify the problem through assessment (we discussed this in the previous session)
Information assessment will help to enable identification of support needs and gaps in service delivery. This will indicate whether or not you need to develop a programme to respond to children’s PSS needs.
Set objectives based on assessment
If you feel there is a need, then you will need to establish what your programme hopes to achieve. This is done through setting objectives.
Do you want or need CFS as part of way to address problem?
CFS are not always the answer, may be other more effective ways to address children’s needs in this context
CFS in most cases should be part of wider programme plans addressing education, protection and mental health and psychosocial support needs
If you decide they are to be part of your programme – then you need to plan the resources, actions, staffing and support you will need to deliver the “a – e” of the CFS approach

## Slide 5: ¿Qué indica que hay necesidad de un CFS?
Notes: Ask participants to give their views on what information gathered through a needs assessment would indicate that Child Friendly Spaces are needed as part of your programme?
After 5mins discussion note the following key points:
Child Friendly Spaces are not the only activity that we might do in an emergency response to protect children. They are one mechanism that enables us to provide immediate and rapid start up of a community-based approach to addressing psychosocial support needs, while allowing us time to find out the more in-depth needs of children and families. They are typically part of a package of supports for children and their families, and they must be seen and presented as such
Yes, need for CFS - Examples of information that indicates a need for CFS programmes:
Children are showing signs of distress
Children are exposed to physical risks due to lack of care for them during the day time
School’s are not in session
Parents are engaged in recovery efforts and are unable to provide care and support needed by children
Certain age group (in range 0 – 18) or category (such as disabled, working children, girls, etc) of children are being excluded from other support activities
No, should not have separate stand-alone CFS activities - Examples of information that indicates a need for CFS programmes:
Pre-existing community groups are running and managing child and adolescent-friendly activities (you may want to support them to do the work they have started)
Schools are continuing lessons and there is little to no evidence of out-of school children (you may wish to support PSS activities in school setting)

## Slide 6: Herramientas para la planificación de programas

## Slide 7: Cruzando el río
Notes: Materials:
20 inches x 20 inches - 50cm x 50cm squares of cardboard, paper or newspaper – you will need about two-thirds as many squares as there are people in the group
Something to demarcate two sides of a river… can be 2 pieces of rope, masking tape, tables, chairs
Set Up:
Create a river by marking two riverbanks with rope, masking tape, chairs, etc. Make the river wide enough to be a challenge for the groups to get from one side to the other (look at about 15 ft. – 4m).
Divide the participants into 3 groups
Spread the groups evenly along the length of the “river”
Distribute the cardboard or paper squares. Each group must have the same ratio of squares of paper to no. of people in the group. Suggest 2/3 as many squares as there are people
Objective:
The objective of the activity is to get all members of their group safely across the river together as fast as possible
First group to get across the river wins
Rules:
They must go as one big group, not multiple smaller ones.
Everyone must be on the river before anyone can get off the river
Participants cannot touch the water (floor/grass) and therefore must use rafts (cardboard squares) to cross.
The water is filled with piranhas. If a person completely comes off the raft they are eaten and since this is a team exercise everyone must start over: "start as a team end as a team.”
No scooting or sliding on the squares
Rafts must be in contact with a human at all times or they will be swept away with the current
Once the group has started the process, the facilitator’s role is to take cardboard squares that are “swept away by the current” and to watch for safety issues

## Slide 8: Interrogantes
¿Cuál era su objetivo?
¿Cómo planificó?
¿Qué trabajó bien?
¿Cuáles eran los desafíos?
¿Los planes cambiaron en la medida que avanzaban?

## Slide 9: Aprendizaje clave de cruzar el río
P: Planifique las acciones desde el principio
A: Agilidad en la implementación
R: Recursos correctamente
C: Coordinar con otros
Notes: Planning before you start helps you to achieve goals and objectives. Taking the time to think through steps needed will save you time later down the line
Be agile: You may want to revisit your plans, and change the way you are working if you find you are not progressing as you would like to. When you face challenges it is good to step back and revisit your plans.
Resource correctly: Resources being staff, materials, space, etc. Assess the resources you have (no. of people, number of squares, distance to cross), and the resources you need when in the planning stage. How will you fill the gaps between the two. [We will discuss this in more detail later]
Coordinate: Learn from others and what they are doing. You could have looked at other teams strategies and improved your technique. Include other teams, agencies and sectors in your planning stage so you can be more efficient with resources and learn from different approaches.

## Slide 10: Objetivos
¿Qué es un objetivo?
Una declaración que expresa lo que espera lograr al hacer algo
¿Porqué se tienen objetivos?
Para estar claros en cuanto a las metas que se quieren lograr a través del proyecto
Para que sea más fácil diseñar el proyecto
Para que sea más fácil presentárselo a otros
Notes: The objectives tell us what we want the impact of the programme to be
When you are planning a journey you do so with your destination in mind, you make the journey in order to achieves something when you get there. So it is with a project. We know where we are now (due to information from assessments). Now we need to begin our work with the end in mind. What is it we want to achieve by carrying out the project? The plan helps us to map out a route, keep track of the aim, make sure we complete each step along the way fully, and track how we get there.
What is an objective?
A statement that expresses what you expect to achieve by doing something
Objectives have two parts: an expression of what is to be achieved and an expression of how it will be achieved. The ends and the means.
A programme or project goal is a general objective - Expresses overall goal of the project. You need to ensure this fits with your organisational plans and objectives. The project cannot wholly achieve this, it is aspiration, and the project should contribute to this.
Purpose is a specific objective – they express ends that are wholly achieved by the activities of the project – when the project is completed, you expect to have achieved the specifc objectives
Why you have objectives?
You have a project in order to have impact on children’s lives. What changes do you intend? What is the project’s purpose? Objectives document this information in one short sentence.
To make it clear to ourselves that the project aims to achieve something intended
To make it easier to design the project – to decide on the what, how, when and how much
To make it easier to present to others so they understand your work and purpose, they support your efforts and collaborate with you and they provide you with funding

## Slide 11: Escribiendo sus objetivos
Contenido de su objetivo:
¿Cuáles son los fines que se quieren lograr?
¿Cuáles son los medios que se usarán?
¿Quienes son los beneficiarios principales / partes interesadas?
¿Cómo se beneficiarán?
Estilo del objetivo:
Que sean SMART (siglas en inglés)
  Específicos, Medibles, Alcanzables, Acordados, Relevantes y en plazos de tiempo
  Escríbalos en una sola oración

## Slide 12: Ejemplo…
Intento | Fines | Medios | Beneficiarios | Cómo se benefician
1 | Reducir el uso de la violencia a niños y niñas en edad escolar | Capacitación | Estudiantes de la escuela | Reducción de la violencia
2 | Reducir el uso y aval de la violencia a niños y niñas en la escuela | Capacitación de maestros y personal administrativo | Estudiantes de la escuela | Reducción de la incidencia de la violencia
3 | Reducir el uso y el aval de la violencia a niños y niñas en las escuelas yy y los distritos xx | Capacitación de maestros y personal administrativo en cuanto a Códigos de Conducto y Leyes de Derechos de la Niñez | Niñas y niños en escuelas yy y distritos xx | Reducción de la incidencia de la violencia y del abuso a niños y niñas en el entorno escolar
Notes: Groups of three work together to develop an objective for CFS project in country – 5mins
A Strengths, weaknesses, opportunities and threats (SWOT) analysis, problem tree or other brainstorming approach can help us to identify the way we want to reach our objective. Giving us an assessment of the causes of the needs and gaps identified during the assessment

## Slide 13: Marco Lógico
 | Resultados | Indicatores | Medios de verificación | Suposiciones
Meta del Proyecto |  |  |  | 
Propósito |  |  |  | 
Objetivo 1 |  |  |  | 
- Resultado 1.1 |  |  |  | 
Objetivo 2 |  |  |  | 
- Objetivo 2.2 |  |  |  | 
Actividades |  |  |  | 
Un marco lógico es una tabla o matriz para la planificación y gestión de proyectos de desarrollo. Presenta información sobre los componentes clave de un proyecto de forma clara, concisa, lógica y sistemática
Notes: A log frame is a tool for planning and managing development projects. It looks like a table or matrix. It presents information about the key components of a project in a clear, concise, logical and systematic way
A log frame summarises, in a standard format:
• What the project is going to achieve?
• What activities will be carried out to achieve its outputs and purpose?
• What resources (inputs) are required?
• What are the potential problems which could affect the success of the project?
• How the progress and ultimate success of the project will be measured and verified?
There should be causality, whereby achieving the sum of the different objectives will enable us to achieve the purpose of the project. The goal is aspirational and goes beyond what the organisation can achieve alone.

## Slide 14: Diagrama de Gantt o planificación de la actividad
Actividad | Sitio | Mes / Semana |  |  |  | Suministros que se necesitan | Personal / socio | Indicador
Poner carpas | N |  |  |  |  | 5 carpas, 1 vehículo | LNGO: Habilitar Niño/Niña | 5 carpas puestas y siendo usadas por 200 niños y niñas; cada una en lugares seguros antes de culminar el mes x
 | S |  |  |  |  |  |  | 
 | E |  |  |  |  |  |  | 
 | W |  |  |  |  | Costo |  | 
 |  |  |  |  |  | USD 5000 por carpa Vehículo: USD 1000 por semana |  | 
Notes: A Gantt chart is a type of bar chart, developed by Henry Gantt that illustrates a project schedule. Gantt charts illustrate the start and finish dates of the main elements and summary elements of a project.

## Slide 15: Actividad de planificación

## Slide 16: Planificación de actividad: programación
Divídase en 6 grupos
1. Coordinación, 2. Dotación de personal, 3. Preparación inicial del CFS, 4. Hacer actividades en el CFS, 5. M&E, 6. Cierre de CFS
Haga una lluvia de idea de acciones clave que debe llevar a cabo
Revise y examine la lista de acciones para su sujeto
  ¿Algunas acciones pueden ser más específicas o concretas?
  ¿Todas las acciones son realistas/posibles?
  ¿Hace falta alguna acción? ¿Se debe eliminar alguna?
Ponga las acciones en el orden en que deben darse
Pegue sus acciones en la pared en el orden que se deben dar (10 min.)

## Slide 17: Planificación de Actividad paso 2: Dotación de recursos
Debajo de cada acción incluya:
Suministros necesarios
Necesidades de personal de apoyo
Logística que se requiere
10 min.

## Slide 18: ¿Ya consideró…?
Tome la lista de acciones preparadas con antelación
  ¿Le hicieron falta algunas acciones?
¿Qué temas transversales deben ser incluidos en las acciones? (Género, VIH/SIDA, niños y niñas con discapacidad, ECD, adolescencia, etc.)
Logística:
  Vehículos – ¿Por cuánto tiempo, dónde, cuándo, alquiler o compra?
  Almacenaje - ¿Por cuánto tiempo y adónde?
  Distribución de materiales
Colaboración con otros sectores, equipos o agencias
Variaciones geográficas
¿Manteniendo los costos bajos? (Valor del dinero)
Notes: Take the list of pre-prepared actions. Were you missing any actions?
What cross-cutting issues need to be included in the actions? (Gender, HIV/AIDS, children with disabilities, ECD, adolescence, etc)
Logistics:
  Vehicles – how long for, where, when, rent or buy?
  Storage - how long for and where?
  Distribution of materials
Collaboration with other sectors, teams or agencies
Geographical variations
Keeping costs down? (Value for money)
In plenary discuss the above questions getting inputs from all the group on if they think they had sufficiently addressed and covered these points and issues?
(10 mins)

## Slide 19: Recursos Clave

## Slide 20: Recursos Clave
Programación y evaluación de programas psicosociales, Alastair Ager
UNICEF, A practical guide for Developing CFS (Una guía práctica para desarrollar CFS)
Bond, The logical framework approach: How To guide, by Greta Jensen, Jan 2012 (El abordaje del marco lógico; Guía del Cómo por Greta Jensen, Enero 2012)

## Slide 21: Resumen de la Sesión

## Slide 22: Recap.
Al final de esta sesión, los participantes…
Conocerán cómo desarrollar objetivos para su programa de Espacios Amigables para Niños y Niñas
Estarán familiarizados con dos marcos / matrices que pueden ayudar en la planificación de programas

## Slide 23: Gracias por escuchar